# IPUMS-Africa I, project details (revised)

Note:  all details will be worked-out on an amicable basis.  As owner of the census data, the national statistical institute (NSI) has final say in case of any disagreement.

- Calendar:  work to be done no earlier than 2005 nor later than 2008, after most of the processing of the 2000-round census is completed and when microdata become workable for drawing a sample.

- Budget:  because the sums are small, no contract is negotiated.  Instead, the Minnesota Population Center (MPC) is billed for a “dissemination license”, which includes not only a license to disseminate harmonized samples, but also copies of the development datasets, essential documentation, and a modest amount of technical advice to clarify documentation.

  - Dissemination license fee:  US$5,000 for each 10% sample supplied ($2,500 for 5% samples or those with fewer than one million person records).  Payments will be made directly to the NSI’s bank account in one lump sum, once the microdata are supplied to the Minnesota Population Center, upon receipt of corresponding invoice.

  - National consultants resident in-country will be contracted to design national microdata integration plans (approximately US$5,000 per census to be integrated).

- Documentation:  provided by NSI, in the national language(s) and in English or French, where available—census enumeration forms, enumerator instructions, technical reports describing census concepts, codes, and operations, etc.

- Samples:  to be drawn by the NSI or the MPC

  - Censuses to be included: every census for which microdata exist. Additional funds are available to recover “historical” census microdata prior to 1990.  Extant datasets no longer in possession of the NSI will be repatriated to the NSI and included in the project.

  - Sample density:  10 percent preferred.

  - Sample method:  simple random.

    - private households:  every tenth household/dwelling after a random start

    - collectives/institutions:  every tenth individual after a random start within each institution; if the sample person is a member of an identifiable family, every member of that person’s family is included.

- Data cleaning and editing:  performed by the NSI or the MPC

- Variables: performed by MPC staff

  - Development datasets: all variables in the original data are provided to the MPC for evaluation purposes.  These datasets are held in the strictest confidence and are not copied or circulated to anyone.

  - Integrated samples:  all variables will be integrated except, for reasons of statistical confidentiality, detailed administrative geography (typically, units with fewer than 10,000 population at latest census).

- Coding:  performed by MPC

  - A detailed analysis is made of the codes and frequencies for each variable.  For “sensitive” variables and codes with small frequencies, these may be suppressed, aggregated or blurred for purposes of confidentiality.

  - For the harmonized samples all released codes are “integrated”, which typically means the original codes are removed and replaced with harmonized codes.

- Anonymization:  by NSI staff or the MPC (we prefer to do this)

  - Analyze every variable and code to identify what anonymization measures need to be taken

  - Aggregate codes of population “uniques”

  - Blurr codes of a small fraction of cases

  - Top and bottom code numeric variables (e.g., income, rent, etc.)

  - Round or truncate detailed codes (e.g. 5 digit ISCO, income, etc.)

  - Swap a small fraction of records across administrative districts to enhance confidentiality

  - Scramble records within administrative districts

  - Other methods may be applied as experience and knowledge dictate.

- Harmonization:  MPC—all variables, all codes, including “derived” variables, such as pointers for spouses, mothers and fathers, etc.

- Dissemination:  MPC via the Internet, free of charge.  Copies of integrated samples will be supplied to the NSI on CD along with documentation for dissemination to national researchers at no cost.